## Sheet1
GROUP-5 INFROG
Process | Start Date | End Date | Duration Day | Status | 2024-08-20 | 2024-08-21 | 2024-08-22 | 2024-08-23 | 2024-08-24 | 2024-08-25 | 2024-08-26 | 2024-08-27 | 2024-08-28 | 2024-08-29 | 2024-08-30 | 2024-08-31
Step 1: Information gathering | 2024-08-20 | 2024-08-31 | 12 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
-Brainstorming
-Research |  |  |  |  | 2024-09-01 | 2024-09-02 | 2024-09-03 | 2024-09-04 | 2024-09-05 | 2024-09-06 | 2024-09-07 | 2024-09-08 | 2024-09-09 | 2024-09-10 | 2024-09-11 | 2024-09-12 | 2024-09-13 | 2024-09-14 | 2024-09-15 | 2024-09-16 | 2024-09-17 | 2024-09-18 | 2024-09-19 | 2024-09-20
Step 2: Planning | 2024-09-01 | 2024-09-20 | 20 | Completed | 2024-09-01: Completed; 2024-09-03: Completed
--
-- |  |  |  |  | 2024-09-21 | 2024-09-22 | 2024-09-23 | 2024-09-24 | 2024-09-25 | 2024-09-26 | 2024-09-27 | 2024-09-28 | 2024-09-29 | 2024-09-30
Step 3: Designing | 2024-09-21 | 2024-09-30 | 10 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
-- | [15 empty] | 0
 | time axis 2024-10-01 to 2024-11-20
Step 4: Content | 2024-10-01 | 2024-11-20 | 51 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
--
[5 empty] | 2024-11-21 | 2024-11-22 | 2024-11-23 | 2024-11-24 | 2024-11-25 | 2024-11-26 | 2024-11-27 | 2024-11-28 | 2024-11-29 | 2024-11-30
Step 5: Testing | 2024-11-21 | 2024-11-30 | 10 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
--
[5 empty] | 2024-12-01 | 2024-12-02 | 2024-12-03 | 2024-12-04 | 2024-12-05 | 2024-12-06 | 2024-12-07 | 2024-12-08 | 2024-12-09 | 2024-12-10
Step 6: Launching | 2024-12-01 | 2024-12-10 | 10 | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
--
Step 7 Monitoring and Updates